MEETING MINUTES

# Quarterly operations review

Decisions, actions, and follow-up

Date and time: August 25, 2026 | 10:00 to 11:00 a.m. PT

Location: Video conference | Operations room

Facilitator: Jordan Lee, Chief Operating Officer

Minutes prepared by: Morgan Chen, Program Operations

Meeting outcome: The team approved the September pilot, assigned owners for the remaining readiness work, and scheduled one final decision review before launch.

# Attendees

| Name | Role | Attendance |
| --- | --- | --- |
| Jordan Lee | Executive sponsor | Present |
| Morgan Chen | Program lead | Present |
| Riley Shah | Operations lead | Present |
| Taylor Brooks | Finance partner | Apologies |

# Agenda

- Confirm pilot readiness and unresolved dependencies.

- Approve launch decisions and assign action owners.

- Set the final review date and distribution list.

# Discussion summary

## Pilot readiness

Configuration and training materials are ready for the pilot group. The remaining dependency is final access approval for two regional supervisors. Operations will use the current escalation path if approval is delayed beyond August 28.

## Measurement and reporting

The team agreed to track completion rate, exception volume, average handling time, and user feedback during the first two weeks. Program Operations will publish a concise daily readout during the pilot and a weekly summary for sponsors.

# Decisions

| ID | Decision | Owner | Effective |
| --- | --- | --- | --- |
| D-01 | Proceed with the September 2 pilot for the approved user group | Jordan Lee | Approved |
| D-02 | Use daily readiness reviews during the first pilot week | Morgan Chen | Sep. 2 |
| D-03 | Escalate unresolved access requests after two business days | Riley Shah | Immediately |

# Action items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Secure access approval for the two regional supervisors | Riley Shah | Aug. 28 | In progress |
| Publish the pilot measurement dashboard and data definitions | Morgan Chen | Aug. 29 | Planned |
| Confirm the support rotation and escalation contacts | Jordan Lee | Aug. 30 | Open |

# Open questions and parking lot

| Topic | Follow-up | Owner |
| --- | --- | --- |
| Post-pilot rollout sequence | Return with options after the first two weeks of evidence | Program lead |
| Long-term dashboard ownership | Confirm the operating owner before production rollout | Operations lead |

# Next meeting

Final readiness review: Monday, August 31, 2026 at 2:00 p.m. PT. Required inputs: access approvals, dashboard link, support rotation, and participant briefing.