WEEKLY PROJECT STATUS REPORT

# Phoenix CRM migration

Status update | Week ending August 21, 2026

Executive sponsor: Jordan Lee, Chief Operating Officer

Project lead: Morgan Chen, Transformation Office

Reporting period: August 17 through August 21, 2026

Overall status: AMBER | Recovery plan active

Overall status: Amber. Core configuration remains on schedule, but data cleansing is five business days behind plan. The recovery actions below protect the pilot date.

# Executive update

The team completed role design, validated the first integration path, and confirmed pilot users. Customer-account cleansing remains the primary schedule risk. Additional data owners were assigned this week, and daily exception reviews begin Monday. No change to approved scope or budget is requested at this time.

# Status by workstream

| Workstream | Status | This period | Next checkpoint |
| --- | --- | --- | --- |
| Platform configuration | Green | Sales stages and access roles approved | Complete workflow testing |
| Data migration | Amber | Duplicate-account rules agreed | Clear 80 percent of exceptions |
| Integrations | Green | Finance connector passed first test | Run end-to-end transaction test |
| Change readiness | Green | Pilot group and training owners confirmed | Publish pilot training schedule |

# This period and next

| Completed this period | Priorities for next period |
| --- | --- |
| Approved the future-state sales process and role matrix | Reduce unresolved customer-account exceptions below 20 percent |
| Validated customer, opportunity, and invoice field mappings | Complete end-to-end testing for the finance integration |
| Confirmed 24 pilot users across sales, service, and finance | Publish pilot training dates, materials, and attendance owners |

# Milestones

| Milestone | Baseline | Forecast | Status |
| --- | --- | --- | --- |
| Configuration complete | Aug. 28, 2026 | Aug. 28, 2026 | Green |
| Data rehearsal complete | Sep. 4, 2026 | Sep. 9, 2026 | Amber |
| Pilot launch | Sep. 14, 2026 | Sep. 14, 2026 | Green |
| Production rollout | Oct. 5, 2026 | Oct. 5, 2026 | Green |

# Risks and issues

| Ref | Risk or issue | Response | Owner and status |
| --- | --- | --- | --- |
| R-04 | Customer-account cleansing is behind plan | Add two data owners and review exceptions daily | Data lead ¦ Open |
| R-07 | Pilot managers have limited training capacity | Offer two live sessions and one recorded option | Change lead ¦ Watching |
| I-02 | One finance test account lacks required permissions | Security team to approve the revised role | Tech lead ¦ Due Aug. 25 |

Decisions required: Approve two temporary regional data owners through September 4, and confirm whether pilot managers may use recorded training when live sessions conflict.

# Action items

| Action | Owner | Due | Status |
| --- | --- | --- | --- |
| Publish daily data-exception dashboard | Data lead | Aug. 24 | In progress |
| Approve revised finance test role | Security | Aug. 25 | Open |
| Release pilot training calendar | Change lead | Aug. 26 | Planned |

Review before distribution: Confirm status ratings, dates, owners, budget statements, and decision requests with the accountable project leaders.