CLIENT PROPOSAL

# A clearer revenue engine for Acme Analytics

Growth strategy and implementation proposal

Prepared for: Acme Analytics

Prepared by: Northstar Studio

Date: August 2026

Sample starter content. Replace it in Word, or publish a reviewed AI draft through BrandQuill.

# Executive summary

Acme Analytics has a strong product and a growing base of satisfied customers, but its acquisition story is fragmented across channels. This proposal turns the existing expertise into one measurable buyer journey, supported by reusable messaging, focused conversion assets, and a practical operating cadence.

Recommendation: Launch a six-week revenue sprint that pairs one high-intent offer with one repeatable proof system and a weekly conversion review.

# Outcomes

- A concise positioning system that sales and marketing can use without rewriting the story for every channel.

- A high-intent landing journey with clear evidence, objections, and calls to action.

- A weekly measurement rhythm that identifies the next best conversion improvement.

# Proposed approach

- Align the offer. Confirm the priority buyer, urgent problem, proof, and commercial outcome.

- Build the journey. Create the core page, supporting proof assets, and conversion follow-up.

- Run the system. Launch, measure qualified behavior, and improve the highest-impact constraint.

# Scope and deliverables

| Phase | Included work | Primary deliverable | Timing |
| --- | --- | --- | --- |
| 01 | Buyer and offer alignment | Positioning brief | Week 1 |
| 02 | Journey and proof design | Conversion page and proof plan | Weeks 2-3 |
| 03 | Launch and measurement | Live campaign and dashboard | Weeks 4-6 |

# Investment and timeline

The engagement is structured as a focused sprint with one accountable outcome. Fees below are sample content and should be replaced with reviewed commercial terms before use.

| Workstream | Delivery | Fee |
| --- | --- | --- |
| Strategy and positioning | Week 1 | $4,000 |
| Journey and conversion assets | Weeks 2-3 | $8,500 |
| Launch and optimization | Weeks 4-6 | $5,500 |

Sample total investment: $18,000, invoiced 50 percent at kickoff and 50 percent at launch.

# Assumptions

- Acme Analytics provides timely access to current messaging, analytics, and approved customer evidence.

- One consolidated review is returned within two business days at each approval point.

- Media spend, external production, and material scope changes are excluded unless added in writing.

# Next steps

- Confirm the scope, commercial terms, and authorized signatories.

- Schedule the kickoff and provide source materials.

- Begin the alignment sprint within five business days of approval.

Review before sending: Verify names, claims, dates, pricing, tax treatment, and contractual language with the appropriate reviewers.