STANDARD OPERATING PROCEDURE

# New client onboarding

From signed agreement to kickoff

| Controlled field | Approved value |
| --- | --- |
| Document owner | Client Operations |
| Version and status | 1.0 ¦ Approved |
| Effective date | September 1, 2026 |
| Review cycle | Every 12 months or after a material process change |
| Approved by | Director of Client Services |

Purpose: Create a complete, accurate, and repeatable handoff from a signed client agreement to a prepared kickoff meeting within five business days.

# Scope

This procedure applies to new retained-service clients after the agreement and initial payment are confirmed. It covers internal setup, information collection, access requests, kickoff preparation, and the final readiness check. Contract review, billing disputes, security exceptions, and implementation delivery follow their separate approved procedures.

# Roles and responsibilities

| Role | Responsibility | Accountability |
| --- | --- | --- |
| Account lead | Own the client relationship, confirm expectations, and lead kickoff | Kickoff readiness |
| Operations coordinator | Create records, request inputs, track access, and maintain evidence | Process completion |
| Finance partner | Confirm payment status and approved billing details | Financial clearance |
| Security owner | Review nonstandard access or data-handling requests | Exception approval |

# Prerequisites and required inputs

- Executed agreement and approved statement of work are stored in the contract repository.

- Initial payment or an approved billing exception is confirmed by Finance.

- Primary client contact, internal account owner, service tier, and target kickoff date are known.

- Any security, privacy, accessibility, or data-residency requirements are identified for review.

# Procedure

- Validate the handoff. Compare the signed agreement, statement of work, pricing record, and sales notes. Resolve conflicting scope, dates, contacts, or commitments before creating the client workspace.

- Create the client record. Enter the legal client name, primary contacts, service tier, billing reference, internal owner, and effective date in the approved system of record.

- Open the onboarding workspace. Create the approved folder structure, project record, communication channel, and onboarding checklist. Apply the correct access group instead of granting access person by person.

- Send the intake request. Use the approved intake message and request only information required for the agreed scope. Give the client one owner, one due date, and one secure submission route.

- Request systems access. Document each requested system, permission level, business purpose, approver, and expiration date. Route nonstandard or privileged access to the Security owner.

- Prepare the kickoff. Draft the agenda, confirmed objectives, success measures, responsibilities, first milestones, risks, decisions needed, and open questions using the approved kickoff template.

- Run the readiness check. Confirm the required inputs, people, systems, and approvals are present. Record gaps, owners, due dates, and any accepted exception.

- Release the kickoff. Send the final agenda and pre-read, update the client record, and notify the internal team only after the readiness criteria are satisfied or an authorized exception is recorded.

Quality gate: Do not represent onboarding as ready while scope conflicts, payment status, required access, or material security questions remain unresolved without a documented owner and authorized exception.

# Quality checks

| Check | Evidence | Owner | Timing |
| --- | --- | --- | --- |
| Scope and commitments match the signed documents | Handoff checklist | Account lead | Before setup |
| Client and billing records contain required fields | System record | Operations | Day 1 |
| Access follows least-privilege and approval rules | Access log | Security owner | Before kickoff |
| Agenda, objectives, owners, and milestones are confirmed | Approved pre-read | Account lead | One day before |

# Exceptions and escalation

| Trigger | Required response | Escalation owner |
| --- | --- | --- |
| Agreement and sales handoff conflict | Pause setup and obtain written scope clarification | Account lead |
| Payment is not confirmed | Pause external kickoff activity or record an approved billing exception | Finance partner |
| Privileged or nonstandard access is requested | Do not grant access until the Security owner approves the request | Security owner |
| Required input will miss the kickoff date | Document impact, propose a new date or reduced agenda, and obtain approval | Client Services director |

# Records and retention

| Record | Approved location | Retention rule | Owner |
| --- | --- | --- | --- |
| Signed agreement and SOW | Contract repository | Per contract policy | Account lead |
| Intake and readiness checklist | Client workspace | Client term plus policy period | Operations |
| Access approvals and exceptions | Access log | Per security policy | Security owner |
| Kickoff agenda and decisions | Client project record | Per records policy | Account lead |

# Approval

| Approval role | Name | Decision | Date |
| --- | --- | --- | --- |
| Process owner | Avery Morgan | Approved | August 25, 2026 |
| Security reviewer | Sam Rivera | Approved | August 25, 2026 |

# Revision history

| Version | Date | Change | Author | Approval |
| --- | --- | --- | --- | --- |
| 0.1 | Aug. 12, 2026 | Initial draft | Client Operations | Draft |
| 0.9 | Aug. 20, 2026 | Added access and exception controls | Client Operations | Review |
| 1.0 | Aug. 25, 2026 | Approved for use | Client Operations | Approved |

# Publication checklist

- Replace every sample name, date, system, owner, threshold, and retention rule.

- Validate the procedure with the people who perform and approve the work.

- Confirm related policies, forms, systems, and escalation routes are current.

- Record formal approval, effective date, document owner, and next review date.

- Publish only in the approved repository and retire obsolete versions.

Required review: This starter is an operational writing aid, not a validated control. BrandQuill formats reviewed content but does not verify safety, legal, security, regulatory, contractual, or process accuracy.